## Sheet1
Milestone # | Milestone Description | Target Date | Deliverables to be completed as part of Milestone
1 | Home Screen | 2018-07-27 | EPPC_PDU_WebUI_Home_Layout_1, EPPC_PDU_WebUI_Home_Mimic_2
2 | Meters List and Meters Navigation | 2018-08-17 | EPPC_PDU_WebUI_Metering_List_3, EPPC_PDU_WebUI_Metering_List_4, EPPC_PDU_WebUI_Metering_List_5
3 | Release | 2018-08-24 | All requirements listed in 4.1
4 | Review, Rework, and Verification | 2018-08-31